
APPENDIX N

SAMPLE IMPLEMENTATION PLANS

INDIANA STATE POLICE

2002 BRICKYARD 400 - TABLE OF CONTENTS

[image: image1.png]TABLE OF CONTENTS

List of Detail Command..................coeuuiineiunieniiniineineeneineineereennns SO 2
Zone #1: Locations, Instructions, and Units Assigned.............c.ccooeviiiiiiinininnn... 3
Zone #2: Locations, Instructions, and Units Assigned..........c...cooiviiiviiiiininin. 3
Zone #3: Locations, Instructions, and Units Assigned............ccccevevinnnennininnnnnnn. 3
Zone #4: Locations, ‘In‘structions, and Units Assigned..............cooovrrviniiiiinnniin, 3
Zone #5: Locations, Instructions, and Units Assigned............cceeveriviiiinininnnninnn 4
Zone #6: Locations, Instructions, and-Uhits Assigned........oooiiiiiiiiiiiiiic i, 4
Telephone NUmbers. ... ..o.vuiniiiiiii e e 5
Court InfOrmation. ... ....c.ouiiiiiiiiir i et e e e eeaeaas 6
INSEIUCHIONS. ... euetiiiiitei sttt 7
Incident Reporting Procedures......;;-...................; ...................................... 7
Operatiﬁg PLOCEAUIES. .. e+ v e e eeeeeeee e eee e ee e e e e e e e s e ees e eses e 8
Zone Commander ReSponsibilities. .. ..ouvveviiiriiiiiiirir i e, 8
-Communication Procedures..............ccocvvvervininiieiiinininnnnn. e e 9
Inter-Agency Responsibilitie_s .................................................................. 10
Location Instructions: Zone #1........c.ccviiiiiiiiiiiiiiiiiieiieiieieieereneneeenens 11
Location Instructions: Zone #2..................... ettt et et et a e ieeare et 18
Location Instructions: Zone #3 ................................................................ 24
Location Instruétions: ZONEHA. ... o e 28
Location Instructions: Zone #5...........cccccevvviininnnnen. e 33
Location INStructions: ZonE H0.......oovviiiieeiiei et te et eeeeeeannreesneeseanesennnns 37
IDOT Operation Plan (Hoosier Helper)........ccouiviriiiiiieiiiiiiiiiiiicceeieeea, 41
Explanation of Speedway Passes...........coeviiiiiiiiiiiiiiiiii i 43
Emergency and Bus Route...........coooiiiiiiiiiii e 44

Prohibited TS, .. oottt e e 45

Alphabetical LiSting. ............coveveeeeeeeeeeeenen., e 46




Source: Indiana State Police

INDIANA DOT

2002 BRICKYARD 400

[image: image2.png]INDIANAPOLIS TRAFFIC MANAGEMENT CENTER
INDIANA DEPARTMENT OF TRANSPORTATION

100 North Senate Avenue A
Room N925 ]_k AE 3 SI
Indianapolis, Indiana 46204-2249 ZY"‘" link to smart trav
(317) 234-0448 - FAX: (317) 233-4662 { '
An Equal Opportunity Employer ® www.trafficwise.org ® www.in.gov/dot é

FRANK O’BANNON, Governor
J. BRYAN NICOL, Commissioner

DATE: 1 August 2002
TO: All INDOT Units Assigned the Brickyard 400 Race Detail

FROM: Jay Wasson, ITS Operations Engineer
Operations Support Division

RE: " Detail Specifics for Brickyard 400 Detail scheduled for Sunday, August 4, 2002

DETAIL OVERVIEW

INDOT through the Greenfield District based ITS program will conduct a race day special detail to facilitate the
movement of persons to and from the Indianapolis Motor Speedway (IMS) via the Interstate System in Marion
County, Indiana. The detail shall consist of the following elements:

e Traveler Information e Motorist Assistance

e Incident Response & Mitigation e Traffic Control, and

¢ System Monitoring (i.e. traffic conditions) e Strategic Planning
DETAIL SCHEDULE

0530 - Command Center Opens at IMS
0600 -INDOT COMMAND operational at IMS Command Center
- AM Interstate Patrol Units 10-41
0630 - INDOT Maintenance to close I-74 Eastbound right lane at I-465
- AM Interstate Patrol Units to be in assigned zone beginning routine patrol.
0700 - Public Gates open at the Indianapolis Motor Speedway
1200 - PM Interstate Patrol Units 10-41
1300 -NASCAR Winston Cup Driver Introductions
- INDOT Maintenance to remove 1-74 lane closure

1330 - Start of Brickyard 400 (160 laps, 400 miles) .
- AM Interstate Patrol Units released from assigned patrol zones and permitted to return to Indianapolis
Sub.

1400 - AM Interstate Patrol Units 10-42

1500 -INDOT maintenance to stage post-race traffic control equipment

1545% - All units assigned to the post-race detail are to be in their assigned locations. (Lap 120 will be the target.)
1800 - Public Gates Close and Indianapolis Motor Speedway

1830% - INDOT COMMAND releases operational control to Indianapolis Traffic Management Center

1930% - PM Interstate Patrol Units released from assigned patrol zones and permitted to return to Indianapolis
Sub.

2000% - PM Interstate Patrol Units and any other 10-41 units for the detail 10-42




[image: image3.png]INDOT Race Day Detail
- Page 2 of 3
® Times may vary due to variability in race duration.

UNIT ASSIGNMENTS
Name i Assignment Radio Number
Holder, Don 38-30 | PM Interstate Patrol 38-30 1200 | 2000
Howe, David 38-41 | AM Interstate Patrol 38-41 0600 1400
Miller, Herb 38-22 | PM Interstate Patrol 38-22 1200 2000
Newland, Mark | X-10 | PM Interstate Patrol (w/ 38-30) 38-30 1200 2000
Roquet, Glenn 38-7 | Command Center — IMS INDOT COMMAND | 0530 | 1830(?)
Silcox, Brian 38-40 | AM Interstate Patrol 38-40 0600 1400
Wasson, Jay 38-1 | Detail Coordinator | 38-1 0530 | 1830(?)
Whuertz, Steve X-9 | Command Center — IMS INDOT COMMAND | 0600 1800
DETAIL SPECIFICS

o All Hoosier Helper FSP Units are assigned to the race day detail are to patrol the West Leg of [-465 from I-
70 (Exit 9) to 56™ Street (Exit 19). If traffic conditions dictate, patrol areas may be expanded at the
discretion of the IMS Command Center.

0 The IMS Command Center console will be known as INDOT Command for all radio traffic. All normal
Hoosier Helper to Base radio traffic with the IMS Command Center is run through the TMC DISPATCH
talkgroup except:

1. The Indianapolis TMC shall be contacted for all private tow requests.
2. The Indianapolis TMC shall be contacted for all abandoned vehicle log interactions.

o All non-critical van-to-van radio traffic should be communicated on DTAG unless the conversation relates
to an active incident in which everyone on the Primary Talkgoup benefits from your insightful dialog. ©

0 During the pre-race and post-race traffic pattern, Hoosier Helpers are to advise INDOT command as to
traffic flow conditions on the mainline and interchange ramps in regular intervals. The IMS Command
Center will be using maps with the 2/10™ Reference Markers, so use the 2/10™ Reference Markers when
communicating this traffic information.

o Units assigned the PM Interstate Patrol Detail are to load as many additional cones into their commissions
as possible. Based on past experience, additional traffic control may be required during the post-race
traffic pattern.

O Interstate Patrol Units that encounter “ticket scalpers” and/or “road side salespersons” are to do the
following: | "

1. Advise INDOT command as to the location and description of the subject(s).

2. Approach the subjects and advise them that pedestrian traffic on the interstate is illegal. While
we do not have enforcement powers, we can most certainly contact someone who does. This
enforcement officer will not be lenient if the subject(s) do not comply with our warning.

3. Advise INDOT command as to the disposition of your conversation.

4. Monitor subject(s) actions as you and other units continue routine patrol of the area.

NOTE: While the City of Speedway does issue permits for these types of activities, the

Interstate Right-of-Way is NOT within the city limits. Therefore, any permit that is flashed

by the subject(s) is null and void on the Interstate!!

REPORT BILLERGENT BEHAVIOR TO THE TMC COMMAND IMMEDIATELY, IF
YOU FEEL THAT YOUR LIFE OR THAT OF OTHERS IS THREATENED!!





[image: image4.png]INDOT Race Day Detail

o Page 3 of 3
A copy of the official traffic pattern map is attached to this memorandum for your information.

State Police units assigned exclusively to the race detail will operate on 52-OPS 2 outside of the track and
52-OPS 1 inside of the track. Due to the Hoosier Helper radios not currently having 52-OPS 1 or 2
programmed, these talkgroups can be monitored in units with onboard scanners as follows:

o System - District 52 Tower

o 52 OPS 1 - Talkgroup ID 16080

o 52 OPS 2 -> Talkgroup ID 16112
District 52 units assigned to routine district duties will continue to operate on 52 Dispatch

SPECIAL ASSIGNMENTS

38-30 and X-10 are to move the temporary DMS from Westbound Crawfordsville Road east of High
School Road to eastbound I-465 east of I-65 on the south side of Indianapolis near mile marker 52.8. This
DMS will be used to advise motorists to watch for stop or slowed traffic ahead due to the road work and
associated traffic congestion on I-74 east of I-465.

38-1 will be escorting a Federal Highway Administration contracted consultant throughout the event. Mr.
Steve Latoski of Dunn Engineering located in New York is studying traffic management for special events.
The results of this study will be used to create a National Guidebook for Special Event Traffic
Management. This is an excellent opportunity for INDOT to help influence the content of a technical
document that will be used all over the county for years to come. Please help to represent INDOT and the
State of Indiana in a professional manner at all times. Your cooperation is appreciated!!

Enclosure — Traffic Pattern Map

CC:

File
TMC Operators




Source: Indiana Department of Transportation

[image: image5.png]ISP- Indianapolis Motor Speedway Traffic Control Map

(See Continuation

Exnt 1

at Right)

T o~ I-465

56 th St. 56 th St.
Local O P
o A
Traffic - 2 \ 71st St
ks S - !
Only (0 5 Exit 124 \\ \8e3 I
= R .
< el
W. 52nd St Entrance to ‘-96 o I-465
@ - Eagle Creek Park Z, - Exit 21
ki % £
o 5
£
7]
_ \
W. 46th St. \
pe) o
m z &/ eona s
S & \,V nd St
o =
N - [e] o
@ = \ Local
e . \ -
%’ B 1-465 X \‘ T;r)a;f;ﬁc‘
; | Exit 20 | y
Z| 5 |
I o @ 1-65
Bxt17 JI\ & | et Exit 123
W.38 St{ _\;é - L-14 W. 38th St. '1 [ = 1-65
=% ===t " — —
L-12 1’ L-13 " I\ 148 L-21ff\L-2 N
L-14C 5 W. 56th St. \
2 L. o \N\© \\LI.I
W. s4tnst. - 14D ( W. 34th S\ Exit19 B\
L-13B L-15 c il . o
T L1580 g [z 9
10 I 2 <
g g  Lse <o o2 =
4y = 2 L-16E I[ = =k B §
4 1-465 % g a4 ji__L-10 Gjio W.
|'74 RN '
Exit 73 Q
AN Parking L-25 |
c1 Drv Run Diversion Creck ™
S -3 W. 25th ;-18 L-19fk
. 736 . . | ] 1
~ S L-34D -
& | M t(no) ISP Traffic Control Location
G-(no.) Gate Number
Inbound Traffic to Track
- Inbound Traffic Diverted to Coke Plant Parkin
W.21st_St. -—Qutbound Traffic ’
<—|-38 — Bus & Taxi Route
at Girls School Rd.
e —
=) Revised: July 1, 2002
(5]
5
£
[ =
Exit 14 2

W. 10th St. \QV?

Grande Av




Federal Highway Administration

U.S. Department of Transportation

400 Seventh Street, S.W. (HOTM)

Washington, D.C. 20590

Toll-Free “Help Line” 866-367-7487

www.ops.fhwa.dot.gov
Publication No. FHWA-OP-04-010

EDL Document No. 13883

NHI Training Course No. 133099

Managing Travel for Planned Special Events

Publication No.: FHWA-NHI-03-120
















































































































































N-6
N-5

